## Table 1
Stage | Task | Tier | Phase | Status | Details/Notes | Source
Reality Check | Oracle (Primary) Integration | Reality vs. Target | Infrastructure Architecture | 🔴 Missing | Target: Chainlink; Reality: Switchboard only (no redundancy) | 1
Reality Check | AI Compute Service | Reality vs. Target | AI Intelligence | 🔴 Missing | Target: AWS + LORA Adapters; Reality: No AI service exists | 1
Reality Check | Backend Security (Helmet/CSP) | Reality vs. Target | Security Hardening | 🔴 Missing | Target: Helmet, CSP, rate-limit; Reality: None installed | 1
Reality Check | Backend Cache (Redis) | Reality vs. Target | Architecture Upgrade | 🔴 Missing | Target: Redis ( $<100$ ms latency); Reality: No Redis | 1
Reality Check | Solana SDK Version | Reality vs. Target | Development Standards | 🟡 Should upgrade | Target: v2; Reality: web3.js v1.98.0 | 1
S0A.1 | Rename frontend/package.json from "spaceape" to "price-bet-frontend" | TIER 0 — FOUNDATION CLEANUP | PHASE 0A: Codebase Identity & Rebrand | 🟢 Done | Cosmetic $\rightarrow$ Trust Signal | 1
S0A.2 | Rename backend/package.json from "prediciton-market-backend" to "price-bet-backend", remove husreo GitHub URLs | TIER 0 — FOUNDATION CLEANUP | PHASE 0A: Codebase Identity & Rebrand | 🟢 Done | Cosmetic $\rightarrow$ Trust Signal | 1
S0A.3 | Update layout.tsx — Price.bet title, SEO meta tags, OpenGraph, Inter font | TIER 0 — FOUNDATION CLEANUP | PHASE 0A: Codebase Identity & Rebrand | 🟢 Done | Cosmetic $\rightarrow$ Trust Signal | 1
S0A.4 | Update backend/src/index.ts — server banner to "Price.bet API \ | GAINR Protocol" | TIER 0 — FOUNDATION CLEANUP | PHASE 0A: Codebase Identity & Rebrand | Not in source | Cosmetic $\rightarrow$ Trust Signal | 1
S0A.5 | Update Cargo.toml program description to "GAINR Protocol — Price.bet Settlement Engine" | TIER 0 — FOUNDATION CLEANUP | PHASE 0A: Codebase Identity & Rebrand | 🟢 Done | Cosmetic $\rightarrow$ Trust Signal | 1
S0A.6 | Consider renaming prediction-market-* folder names to price-bet-* (optional, monorepo) | TIER 0 — FOUNDATION CLEANUP | PHASE 0A: Codebase Identity & Rebrand | ⚪ Not Started | Cosmetic $\rightarrow$ Trust Signal | 1
S0B.1 | Implement Solana wallet signature verification middleware (tweetnacl + bs58) on all POST endpoints | TIER 0 — FOUNDATION CLEANUP | PHASE 0B: Security Foundation | 🟢 Done | Critical — 24–48hr | 1
S0B.2 | Remove hardcoded BREAK_GLASS_CODE fallback ("GAINR_EMERGENCY_2026") — env-only, crash if missing | TIER 0 — FOUNDATION CLEANUP | PHASE 0B: Security Foundation | 🟢 Done | Critical — 24–48hr | 1
S0B.3 | Replace string !== comparison with crypto.timingSafeEqual() in Break-Glass auth | TIER 0 — FOUNDATION CLEANUP | PHASE 0B: Security Foundation | 🟢 Done | Critical — 24–48hr | 1
S0B.4 | Add helmet middleware (HTTP security headers: CSP, HSTS, X-Frame-Options) | TIER 0 — FOUNDATION CLEANUP | PHASE 0B: Security Foundation | 🟢 Done | Critical — 24–48hr | 1
S0B.5 | Add express-rate-limit + express-slow-down (DoS protection) | TIER 0 — FOUNDATION CLEANUP | PHASE 0B: Security Foundation | 🟢 Done | Critical — 24–48hr | 1
S0B.6 | Fix betting controller — stop trusting token_a_price / token_b_price from client body; fetch truth from Solana on-chain | TIER 0 — FOUNDATION CLEANUP | PHASE 0B: Security Foundation | 🟢 Done | Critical — 24–48hr | 1
S0B.7 | Reduce express.json({ limit }) from 50mb $\rightarrow$ 1mb | TIER 0 — FOUNDATION CLEANUP | PHASE 0B: Security Foundation | 🟢 Done | Critical — 24–48hr | 1
S0B.8 | Add Zod request body validation schemas on all API routes | TIER 0 — FOUNDATION CLEANUP | PHASE 0B: Security Foundation | 🟢 Done | Critical — 24–48hr | 1
S1.1 | Apply NonTransferable + DefaultAccountState::Frozen extensions to $GBET mint in init_bet_mint.rs | TIER 1 — CORE INFRASTRUCTURE | PHASE 1: $GBET Ecosystem & Token-2022 | 🟢 Done | Not in source | 1
S1.2 | Player Vault: USDC $\rightarrow$ $GBET Minting (deposit_usdc.rs) | TIER 1 — CORE INFRASTRUCTURE | PHASE 1: $GBET Ecosystem & Token-2022 | 🟢 Correct | Token-2022 CPI correct | 1
S1.3 | Withdrawal: $GBET Burn $\rightarrow$ USDC Release (withdraw_usdc.rs) | TIER 1 — CORE INFRASTRUCTURE | PHASE 1: $GBET Ecosystem & Token-2022 | 🟢 Correct | Token-2022 CPI correct | 1
S1.4 | Fix betting.rs — update to transfer_checked CPI for Token-2022 (currently causes mismatch error) | TIER 1 — CORE INFRASTRUCTURE | PHASE 1: $GBET Ecosystem & Token-2022 | 🟢 Done | Identified as legacy import in audit findings | 1
S1.5 | Fix sell_shares.rs — update to transfer_checked CPI for Token-2022 | TIER 1 — CORE INFRASTRUCTURE | PHASE 1: $GBET Ecosystem & Token-2022 | 🟢 Done | Identified as legacy import in audit findings | 1
S1.6 | Fix token_mint.rs for Token-2022 compatibility (mint_to CPI) | TIER 1 — CORE INFRASTRUCTURE | PHASE 1: $GBET Ecosystem & Token-2022 | 🟢 Done | Not in source | 1
S1.7 | Regenerate Anchor IDL + Frontend SDK after Token-2022 fixes | TIER 1 — CORE INFRASTRUCTURE | PHASE 1: $GBET Ecosystem & Token-2022 | ⚪ Not Started | Not in source | 1
S1.8 | Devnet integration test — full cycle: Deposit USDC $\rightarrow$ Get $GBET $\rightarrow$ Place Bet $\rightarrow$ Sell $\rightarrow$ Withdraw | TIER 1 — CORE INFRASTRUCTURE | PHASE 1: $GBET Ecosystem & Token-2022 | ⚪ Not Started | Not in source | 1
S2.1 | CPMM $x \times y = k$ swap logic in betting.rs (lines 202–265) | TIER 1 — CORE INFRASTRUCTURE | PHASE 2: CPMM Trading Engine | 🟡 Partial | math present but net_amount / total_collateral_added mixing is inconsistent | 1
S2.2 | Cash Out: sell_shares.rs CPMM inverse | TIER 1 — CORE INFRASTRUCTURE | PHASE 2: CPMM Trading Engine | 🟡 Partial | uses f64 sqrt (line 113), should use integer sqrt for determinism | 1
S2.3 | LP Fee Distribution (pool_fee_percentage in Global) | TIER 1 — CORE INFRASTRUCTURE | PHASE 2: CPMM Trading Engine | 🟡 Partial | fee taken, distribution path unverified | 1
S2.4 | Fix set_token_price() placeholder — replaced with CPMM compute_prices() | TIER 1 — CORE INFRASTRUCTURE | PHASE 2: CPMM Trading Engine | 🟢 Done | Not in source | 1
S2.5 | Add checked_ arithmetic everywhere + replace as u64 casts with try_into() | TIER 1 — CORE INFRASTRUCTURE | PHASE 2: CPMM Trading Engine | 🟢 Done | Not in source | 1
S2.6 | Devnet trading stress test — buy/sell sequence, verify price_a + price_b = 10,000 bps invariant | TIER 1 — CORE INFRASTRUCTURE | PHASE 2: CPMM Trading Engine | ⚪ Not Started | Not in source | 1
S3.1 | zkMe SDK Frontend Integration (@zkmelabs/widget: ^0.3.6, ZKMeProvider.tsx) | TIER 2 — COMPLIANCE & INTELLIGENCE | PHASE 3: Identity & Regulatory Layer (GLI-33 Pathway) | 🟡 Partial | widget renders, no on-chain link | 1
S3.2 | Real on-chain ZK-Proof Validation via Solana ed25519 precompile — replace 3-byte dummy (1) in betting.rs | TIER 2 — COMPLIANCE & INTELLIGENCE | PHASE 3: Identity & Regulatory Layer (GLI-33 Pathway) | 🟢 Done | State defined + PDA enforced | 1
S3.3 | Token ACL — DefaultAccountState::Frozen on $GBET, thaw only after ZK-SBT verification | TIER 2 — COMPLIANCE & INTELLIGENCE | PHASE 3: Identity & Regulatory Layer (GLI-33 Pathway) | 🟡 In Progress | Not in source | 1
S3.4 | Geo-fencing Middleware (IP filtering) — controller exists, needs production IP database | TIER 2 — COMPLIANCE & INTELLIGENCE | PHASE 3: Identity & Regulatory Layer (GLI-33 Pathway) | 🟡 Unverified | Not in source | 1
S3.5 | Break-Glass PII Enclave — fix hardcoded secret (S0B.2), add encrypted PII storage with timing-safe auth | TIER 2 — COMPLIANCE & INTELLIGENCE | PHASE 3: Identity & Regulatory Layer (GLI-33 Pathway) | 🔴 Needs Fix | Not in source | 1
S3.6 | Daily Hash-Digest — on-chain immutability proof for regulators | TIER 2 — COMPLIANCE & INTELLIGENCE | PHASE 3: Identity & Regulatory Layer (GLI-33 Pathway) | ⚪ Not Started | Not in source | 1
S3.7 | Off-Chain Regulatory Indexer — CSV/XLS export for GLI-33 audit reports | TIER 2 — COMPLIANCE & INTELLIGENCE | PHASE 3: Identity & Regulatory Layer (GLI-33 Pathway) | ⚪ Not Started | Not in source | 1
S4.1 | Deploy gainr-ai-oracle Python FastAPI microservice — accepts market ID, returns fair-value probability | TIER 2 — COMPLIANCE & INTELLIGENCE | PHASE 4: AI Reasoning & Data Insight (System-2 Intelligence) | ⚪ Not Started | Separate Python/FastAPI microservice | 1
S4.2 | Wire oracle/index.ts backend controller $\rightarrow$ REST call to gainr-ai-oracle service | TIER 2 — COMPLIANCE & INTELLIGENCE | PHASE 4: AI Reasoning & Data Insight (System-2 Intelligence) | ⚪ Not Started | Not in source | 1
S4.3 | Real-time Market Opportunity Alerts (Edge $> 5\%$ ) via WebSocket/SSE push | TIER 2 — COMPLIANCE & INTELLIGENCE | PHASE 4: AI Reasoning & Data Insight (System-2 Intelligence) | ⚪ Not Started | Not in source | 1
S4.4 | Syndicate Data Feed (PGI) — secure pipeline from Gainr Analytics $\rightarrow$ PostgreSQL data lake | TIER 2 — COMPLIANCE & INTELLIGENCE | PHASE 4: AI Reasoning & Data Insight (System-2 Intelligence) | ⚪ Not Started | Not in source | 1
S4.5 | L2 Predictive Model — LORA fine-tuned on syndicate data (HuggingFace PEFT + PyTorch) | TIER 2 — COMPLIANCE & INTELLIGENCE | PHASE 4: AI Reasoning & Data Insight (System-2 Intelligence) | ⚪ Not Started | Not in source | 1
S4.6 | L3 Hybrid RAG Pipeline — real-time news context (injury/weather/social) via LangChain | TIER 2 — COMPLIANCE & INTELLIGENCE | PHASE 4: AI Reasoning & Data Insight (System-2 Intelligence) | ⚪ Not Started | Not in source | 1
S4.7 | L4 System-2 EV Reasoning Engine — multi-model ensemble with confidence scoring | TIER 2 — COMPLIANCE & INTELLIGENCE | PHASE 4: AI Reasoning & Data Insight (System-2 Intelligence) | ⚪ Not Started | Not in source | 1
S5.1 | Add Redis — session tokens, market data cache, rate-limiting state (target: $<50$ ms auth latency) | TIER 3 — ARCHITECTURE TRANSFORMATION & UX | PHASE 5: Backend Architecture Upgrade | ⚪ Not Started | Target: $<50$ ms auth latency | 1
S5.2 | Add WebSocket layer (Socket.io or ws) — real-time social ticker + AI alerts delivery | TIER 3 — ARCHITECTURE TRANSFORMATION & UX | PHASE 5: Backend Architecture Upgrade | ⚪ Not Started | Not in source | 1
S5.3 | Add BullMQ + Redis job queue — on-chain event processing (BettingEvent $\rightarrow$ DB update $\rightarrow$ alert trigger) | TIER 3 — ARCHITECTURE TRANSFORMATION & UX | PHASE 5: Backend Architecture Upgrade | ⚪ Not Started | Not in source | 1
S5.4 | Evaluate NestJS migration — structured modules, DI, Guards (auth), Interceptors, auto-OpenAPI docs | TIER 3 — ARCHITECTURE TRANSFORMATION & UX | PHASE 5: Backend Architecture Upgrade | ⚪ Not Started | Not in source | 1
S5.5 | Add SWR or TanStack Query on frontend — replace raw axios with intelligent cache/revalidation | TIER 3 — ARCHITECTURE TRANSFORMATION & UX | PHASE 5: Backend Architecture Upgrade | ⚪ Not Started | Not in source | 1
S5.6 | Upgrade @solana/web3.js v1 $\rightarrow$ v2 across frontend and backend (tree-shakeable, smaller bundles) | TIER 3 — ARCHITECTURE TRANSFORMATION & UX | PHASE 5: Backend Architecture Upgrade | ⚪ Not Started | Not in source | 1
S6.1 | Full Price.bet Dark Mode + Glassmorphism Design System | TIER 3 — ARCHITECTURE TRANSFORMATION & UX | PHASE 6: Professional Trading UI | ⚪ Not Started | Not in source | 1
S6.2 | Advanced Charts — candlestick probability curves + volume bars | TIER 3 — ARCHITECTURE TRANSFORMATION & UX | PHASE 6: Professional Trading UI | ⚪ Not Started | Not in source | 1
S6.3 | Real-time Social Win/Bet Ticker Overlay (WebSocket backend from S5.2) | TIER 3 — ARCHITECTURE TRANSFORMATION & UX | PHASE 6: Professional Trading UI | ⚪ Not Started | Not in source | 1
S6.4 | AI Insight Panel — Fair Value display, Edge indicator, Opportunity alerts card | TIER 3 — ARCHITECTURE TRANSFORMATION & UX | PHASE 6: Professional Trading UI | ⚪ Not Started | Not in source | 1
S6.5 | Mobile PWA manifest + offline support + service worker | TIER 3 — ARCHITECTURE TRANSFORMATION & UX | PHASE 6: Professional Trading UI | ⚪ Not Started | Not in source | 1
S6.6 | Web Vitals optimization — LCP $< 2.5$ s, CLS $< 0.1$ , FID $< 100$ ms | TIER 3 — ARCHITECTURE TRANSFORMATION & UX | PHASE 6: Professional Trading UI | ⚪ Not Started | Not in source | 1
S6.7 | Frontend code splitting — lazy load wallet adapter, route-based chunking | TIER 3 — ARCHITECTURE TRANSFORMATION & UX | PHASE 6: Professional Trading UI | ⚪ Not Started | Not in source | 1
S7.1 | Squads Protocol multi-sig for admin key — no single-key control of user funds or parameters | TIER 4 — SECURITY & PRODUCTION HARDENING | PHASE 7: Smart Contract Security | ⚪ Not Started | Not in source | 1
S7.2 | Program upgrade authority $\rightarrow$ multi-sig (prevents rogue upgrade) | TIER 4 — SECURITY & PRODUCTION HARDENING | PHASE 7: Smart Contract Security | ⚪ Not Started | Not in source | 1
S7.3 | Time-lock on privileged instructions (resolve_market 24hr delay + dispute window) | TIER 4 — SECURITY & PRODUCTION HARDENING | PHASE 7: Smart Contract Security | ⚪ Not Started | Not in source | 1
S7.4 | Replace all /// CHECK: UncheckedAccount with explicit PDA derivation constraints | TIER 4 — SECURITY & PRODUCTION HARDENING | PHASE 7: Smart Contract Security | ⚪ Not Started | Not in source | 1
S7.5 | Dual independent security audit (OtterSec + Zellic / Neodyme / Trail of Bits) | TIER 4 — SECURITY & PRODUCTION HARDENING | PHASE 7: Smart Contract Security | ⚪ Not Started | Not in source | 1
S8.1 | CI/CD Pipeline (GitHub Actions) | TIER 4 — SECURITY & PRODUCTION HARDENING | PHASE 8: Infrastructure & DevOps | ⚪ Not Started | Lint $\rightarrow$ TypeCheck $\rightarrow$ Unit $\rightarrow$ Anchor Build $\rightarrow$ Devnet Deploy $\rightarrow$ Integration $\rightarrow$ Manual Gate $\rightarrow$ Mainnet | 1
S8.2 | Infrastructure as Code (Terraform / AWS CDK) for cloud infra | TIER 4 — SECURITY & PRODUCTION HARDENING | PHASE 8: Infrastructure & DevOps | ⚪ Not Started | Not in source | 1
S8.3 | Monitoring: Grafana + Prometheus (backend metrics: req/s, error rate, latency) | TIER 4 — SECURITY & PRODUCTION HARDENING | PHASE 8: Infrastructure & DevOps | ⚪ Not Started | Not in source | 1
S8.4 | Sentry integration — frontend + backend error tracking with source maps | TIER 4 — SECURITY & PRODUCTION HARDENING | PHASE 8: Infrastructure & DevOps | ⚪ Not Started | Not in source | 1
S8.5 | Helius Webhooks — on-chain event streaming (replace RPC polling) | TIER 4 — SECURITY & PRODUCTION HARDENING | PHASE 8: Infrastructure & DevOps | ⚪ Not Started | Not in source | 1
S8.6 | PagerDuty / OpsGenie alerting (on-call rotation for production incidents) | TIER 4 — SECURITY & PRODUCTION HARDENING | PHASE 8: Infrastructure & DevOps | ⚪ Not Started | Not in source | 1
S8.7 | Smart contract monitoring — abnormal bet sizes, oracle failures, vault solvency ratio | TIER 4 — SECURITY & PRODUCTION HARDENING | PHASE 8: Infrastructure & DevOps | ⚪ Not Started | Not in source | 1
S8.8 | AWS Secrets Manager — move ALL env vars out of .env files | TIER 4 — SECURITY & PRODUCTION HARDENING | PHASE 8: Infrastructure & DevOps | ⚪ Not Started | Not in source | 1
S8.9 | VPC + private subnets for MongoDB/Redis (DB never publicly accessible) | TIER 4 — SECURITY & PRODUCTION HARDENING | PHASE 8: Infrastructure & DevOps | ⚪ Not Started | Not in source | 1
S8.10 | WAF (Cloudflare or AWS) — Layer 7 DDoS protection in front of API | TIER 4 — SECURITY & PRODUCTION HARDENING | PHASE 8: Infrastructure & DevOps | ⚪ Not Started | Not in source | 1
S9.1 | 2,000+ TPS load testing (k6 or Artillery against API + Solana devnet) | TIER 4 — SECURITY & PRODUCTION HARDENING | PHASE 9: Performance Engineering | ⚪ Not Started | Not in source | 1
S9.2 | Versioned Transactions (V0) + Address Lookup Tables for all complex instructions | TIER 4 — SECURITY & PRODUCTION HARDENING | PHASE 9: Performance Engineering | ⚪ Not Started | Not in source | 1
S9.3 | Jito MEV bundles activation for high-value bets (dependency already in package.json) | TIER 4 — SECURITY & PRODUCTION HARDENING | PHASE 9: Performance Engineering | ⚪ Not Started | Not in source | 1
S9.4 | Horizontal scaling — stateless Express/Fastify behind Nginx or AWS ECS/Fargate | TIER 4 — SECURITY & PRODUCTION HARDENING | PHASE 9: Performance Engineering | ⚪ Not Started | Not in source | 1
S9.5 | Redis Cluster (not single node) for production failover | TIER 4 — SECURITY & PRODUCTION HARDENING | PHASE 9: Performance Engineering | ⚪ Not Started | Not in source | 1
S9.6 | MongoDB Atlas read replicas for market data reads | TIER 4 — SECURITY & PRODUCTION HARDENING | PHASE 9: Performance Engineering | ⚪ Not Started | Not in source | 1
S9.7 | CDN (Cloudflare) for static market metadata edge caching | TIER 4 — SECURITY & PRODUCTION HARDENING | PHASE 9: Performance Engineering | ⚪ Not Started | Not in source | 1
S9.8 | Next.js Server Components — use RSC for market lists to reduce client JS bundle | TIER 4 — SECURITY & PRODUCTION HARDENING | PHASE 9: Performance Engineering | ⚪ Not Started | Not in source | 1
S10.1 | Deploy $GAINR Token — 100M fixed supply, standard SPL Token | TIER 5 — ECOSYSTEM EXPANSION | PHASE 10: $GAINR Utility Token & Tokenomics Engine | ⚪ Not Started | Not in source | 1
S10.2 | Buyback-and-Burn Engine ( $20\%$ of protocol revenue) | TIER 5 — ECOSYSTEM EXPANSION | PHASE 10: $GAINR Utility Token & Tokenomics Engine | ⚪ Not Started | Not in source | 1
S10.3 | Fee Discount Tiers — Bronze ( $5\%$ ), Silver ( $10\%$ ), Gold ( $25\%$ ) based on $GAINR holdings | TIER 5 — ECOSYSTEM EXPANSION | PHASE 10: $GAINR Utility Token & Tokenomics Engine | ⚪ Not Started | Not in source | 1
S10.4 | Vesting contracts — Seed (6mo cliff, 24mo vest), Team (12mo cliff, 18mo vest) | TIER 5 — ECOSYSTEM EXPANSION | PHASE 10: $GAINR Utility Token & Tokenomics Engine | ⚪ Not Started | Not in source | 1
S10.5 | On-chain governance — fee parameters, oracle keys, reserve ratios controlled by $GAINR holders | TIER 5 — ECOSYSTEM EXPANSION | PHASE 10: $GAINR Utility Token & Tokenomics Engine | ⚪ Not Started | Not in source | 1
S11.1 | Parimutuel Betting Smart Contract (dividend = pool / winning stake) | TIER 5 — ECOSYSTEM EXPANSION | PHASE 11: Back.bet (P2P Sports Betting Engine) | ⚪ Not Started | Not in source | 1
S11.2 | LaaS PID Controller — automatic pool rebalancing using treasury reserves | TIER 5 — ECOSYSTEM EXPANSION | PHASE 11: Back.bet (P2P Sports Betting Engine) | ⚪ Not Started | Not in source | 1
S11.3 | Reserve Quoter — signed off-chain quotes, MEV/front-running protection | TIER 5 — ECOSYSTEM EXPANSION | PHASE 11: Back.bet (P2P Sports Betting Engine) | ⚪ Not Started | Not in source | 1
S11.4 | Exposure Manager — $15\%$ Risk of Ruin atomic circuit breaker | TIER 5 — ECOSYSTEM EXPANSION | PHASE 11: Back.bet (P2P Sports Betting Engine) | ⚪ Not Started | Not in source | 1
S11.5 | Back.bet Frontend — sports market UI | TIER 5 — ECOSYSTEM EXPANSION | PHASE 11: Back.bet (P2P Sports Betting Engine) | ⚪ Not Started | Not in source | 1
S12.1 | Signal Provider Smart Contract (staking + reputation system) | TIER 5 — ECOSYSTEM EXPANSION | PHASE 12: Pick.bet & B2B API | ⚪ Not Started | Not in source | 1
S12.2 | Copy-Trade Execution Engine | TIER 5 — ECOSYSTEM EXPANSION | PHASE 12: Pick.bet & B2B API | ⚪ Not Started | Not in source | 1
S12.3 | Pick.bet Frontend — signal marketplace UI | TIER 5 — ECOSYSTEM EXPANSION | PHASE 12: Pick.bet & B2B API | ⚪ Not Started | Not in source | 1
S12.4 | B2B "Bloomberg for Betting" API — sell liquidity/odds to Web2 operators via paid OpenAPI | TIER 5 — ECOSYSTEM EXPANSION | PHASE 12: Pick.bet & B2B API | ⚪ Not Started | Not in source | 1
S12.5 | SDK published to NPM for B2B partner self-integration | TIER 5 — ECOSYSTEM EXPANSION | PHASE 12: Pick.bet & B2B API | ⚪ Not Started | Not in source | 1
S13.1 | Chainlink Oracle Integration (alongside Switchboard for redundant result verification) | TIER 5 — ECOSYSTEM EXPANSION | PHASE 13: Integrations & Go-Live | ⚪ Not Started | Not in source | 1
S13.2 | BVNK Fiat On-Ramp (Stripe/Skrill/Bank Transfer for non-crypto users) | TIER 5 — ECOSYSTEM EXPANSION | PHASE 13: Integrations & Go-Live | ⚪ Not Started | Not in source | 1
S13.3 | Web2 OIDC / Social Login (account abstraction for non-crypto natives) | TIER 5 — ECOSYSTEM EXPANSION | PHASE 13: Integrations & Go-Live | ⚪ Not Started | Not in source | 1
S13.4 | Syndicate Pro Terminal — institutional low-latency trading UI | TIER 5 — ECOSYSTEM EXPANSION | PHASE 13: Integrations & Go-Live | ⚪ Not Started | Not in source | 1
S13.5 | Squads Protocol multi-sig treasury governance activation | TIER 5 — ECOSYSTEM EXPANSION | PHASE 13: Integrations & Go-Live | ⚪ Not Started | Not in source | 1
S13.6 | Mainnet deployment — all three dApps live | TIER 5 — ECOSYSTEM EXPANSION | PHASE 13: Integrations & Go-Live | ⚪ Not Started | Not in source | 1
S14.1 | Crypto-friendly jurisdiction company structure (Cayman / BVI / Gibraltar) | TIER 5 — ECOSYSTEM EXPANSION | PHASE 14: Legal & Compliance Certification | ⚪ Not Started | Not in source | 1
S14.2 | UK / Malta gambling license application (12–18 month process) | TIER 5 — ECOSYSTEM EXPANSION | PHASE 14: Legal & Compliance Certification | ⚪ Not Started | Not in source | 1
S14.3 | Howey Test legal opinion letter ($GBET non-transferable, $GAINR utility) | TIER 5 — ECOSYSTEM EXPANSION | PHASE 14: Legal & Compliance Certification | ⚪ Not Started | Not in source | 1
S14.4 | ISO 27001 + ISO 42001 architecture alignment documentation | TIER 5 — ECOSYSTEM EXPANSION | PHASE 14: Legal & Compliance Certification | ⚪ Not Started | Not in source | 1
S14.5 | Gitbook documentation — full API reference, smart contract NatSpec, integration guides | TIER 5 — ECOSYSTEM EXPANSION | PHASE 14: Legal & Compliance Certification | ⚪ Not Started | Not in source | 1

## Source References
Index | Reference
1 | GOALS4.md